The whole computational stack of ml :
Yes. For your specification, I would make this the master computational specification: every quantity that the system calculates anywhere in the platform, including tiny intermediate features that feed another calculation.

The key principle is:

Use deterministic formulas/statistics whenever the quantity is directly derivable from observed data. Use ML only when the system must learn a relationship and predict an unknown future outcome.

So you should not use ML for things like cost escalation, expenditure %, elapsed time, rankings, averages, etc. That would make the system less transparent and harder to defend.

Master Computational Specification

0. Overall computational architecture

Your system should work approximately as:

Raw PAIMANA Data

↓

Data Cleaning / Validation

↓

Project-Level Derived Features

↓

Historical / Temporal Features

↓

Statistical Indicators

↓

ML Predictions

↓

Risk Engine

↓

Warning Engine

↓

Intervention Priority

↓

Dashboard Aggregations / Rankings

There are therefore five major types of computation:

| Type | Best method | Purpose |
| --- | --- | --- |
| Direct calculation | Formula | Derive something exactly from available data |
| Aggregation | Statistical aggregation | Summarize projects |
| Temporal analysis | Rolling statistics / trend analysis | Understand deterioration/change |
| Prediction | ML | Predict an unknown future outcome |
| Decision/risk logic | Transparent rules/formulas | Convert evidence into risk/action |

PART A — BASIC PROJECT CALCULATIONS

These are the smallest building blocks. Almost everything else depends on them.

1. Project duration

Calculation:

Planned Duration=Planned Completion Date-Project Start Date

Method

Formula

Why

It is directly observable from dates. There is nothing to learn.

2. Elapsed project duration

Elapsed Duration=Current Date-Start Date

Method

Formula

Why

Exact deterministic calculation.

3. Remaining planned duration

Remaining Duration=Planned Completion Date-Current Date

Method

Formula

Why

Directly calculated.

4. Time elapsed %

Time Elapsed%=Elapsed DurationPlanned Duration×100

Method

Formula

Why

Shows how much of the planned project timeline has passed.

5. Time remaining %

Time Remaining%=100-Time Elapsed%

Method

Formula

PART B — COST CALCULATIONS

6. Absolute cost escalation

Cost Escalation=Latest Revised Cost-Original Approved Cost

Method

Formula

Why

This is an exact accounting difference.

7. Cost escalation %

Cost Escalation%=Revised Cost-Original CostOriginal Cost×100

Method

Formula

Why

Standard normalized measure allowing projects of different sizes to be compared.

8. Cost growth factor

Cost Growth Factor=Revised CostOriginal Cost

Method

Formula

Useful internally for modelling.

9. Expenditure %

Expenditure%=Cumulative ExpenditureLatest Relevant Cost×100

Method

Formula

The denominator should be explicitly defined—typically the latest approved/revised cost depending on the PAIMANA field semantics.

10. Remaining financial exposure

Remaining Exposure=Latest Cost-Cumulative Expenditure

Method

Formula

Why

Shows how much approved project expenditure remains.

11. Cost overrun amount

For a project whose final/revised cost is known:

Cost Overrun=Final Cost-Original Cost

Method

Formula

This becomes an outcome/target variable for ML training.

12. Cost overrun %

Cost Overrun%=Final Cost-Original CostOriginal Cost×100

Method

Formula

Again, this is the actual historical outcome.

PART C — PHYSICAL & FINANCIAL PROGRESS

13. Physical progress %

If directly reported:

Physical Progress=PAIMANA reported value

Method

Source value

Do not build an ML model to estimate this if PAIMANA already reports it.

14. Financial progress %

If the system needs to derive it:

Financial Progress%=Cumulative ExpenditureRelevant Project Cost×100

Method

Formula

Use the source's official definition if PAIMANA already provides financial progress.

15. Physical–financial progress gap

Progress Gap=Physical Progress%-Financial Progress%

Method

Formula

Interpretation

Large positive value:

Physical work is ahead relative to expenditure.

Large negative value:

Expenditure is ahead relative to physical completion.

This is an important diagnostic feature.

16. Absolute progress divergence

∣Physical Progress-Financial Progress∣

Method

Formula

Useful when you care about the magnitude of divergence rather than direction.

PART D — PLANNED VS ACTUAL PROGRESS

This requires a baseline for what progress should have been by the current date.

17. Expected progress

A simple baseline can be:

Expected Progress=Elapsed DurationPlanned Duration×100

bounded between 0–100%.

Method

Formula

Important nuance

This is only a time-based baseline, not necessarily the project's actual milestone schedule.

If PAIMANA provides milestone-level or planned-progress information, use that instead.

18. Progress deviation

Progress Deviation=Actual Physical Progress-Expected Progress

Method

Formula

Interpretation

- Positive → ahead of baseline

- Negative → behind baseline

19. Progress delay %

Progress Delay%=Expected Progress-Actual ProgressExpected Progress×100

Method

Formula

Useful for normalization.

20. Progress completion ratio

Progress Completion Ratio=Actual ProgressExpected Progress

Method

Formula

A ratio below 1 indicates underperformance relative to the simple baseline.

PART E — VELOCITY / RATE CALCULATIONS

These become especially useful with monthly PAIMANA data.

21. Physical progress velocity

For two reporting periods:

Physical Velocity=Pt-Pt-1Timet-Timet-1

Usually expressed as percentage points/month.

Method

Formula

22. Financial expenditure velocity

Expenditure Velocity=Et-Et-1Timet-Timet-1

Method

Formula

23. Progress acceleration

Progress Acceleration=Velocityt-Velocityt-1

Method

Formula

Why

Velocity tells you whether progress is happening.

Acceleration tells you whether the rate itself is improving or deteriorating.

24. Expenditure acceleration

Expenditure Acceleration=ExpenditureVelocityt-ExpenditureVelocityt-1

Method

Formula

PART F — TREND & DETERIORATION

These should generally be statistical, not ML.

25. Recent physical-progress trend

Fit a simple linear trend over recent observations:

Progresst=a+bt

where bis the trend/slope.

Method

Linear regression / statistical trend

Why

You're not trying to predict final project success here.

You're asking:

Is this project's progress trajectory improving or deteriorating?

A simple slope is transparent and robust.

26. Recent expenditure trend

Same concept:

Expendituret=a+bt

Method

Statistical trend

27. Moving average of progress

For example, 3-month:

MA3=Pt+Pt-1+Pt-23

Method

Rolling statistical calculation

28. Moving average of expenditure

Same approach.

Method

Rolling statistical calculation

29. Change in moving average

MAChange=MArecent-MAprevious

Method

Formula + rolling statistics

Useful for detecting deterioration.

30. Progress volatility

For recent monthly progress changes:

Volatility=StdDevΔProgress

Method

Standard deviation

Why

A project with highly unstable progress may deserve more attention even if its average progress looks acceptable.

31. Expenditure volatility

Same methodology.

Method

Standard deviation

32. Deterioration score

Rather than inventing another ML model, combine standardized indicators such as:

- declining progress trend

- declining velocity

- worsening progress deviation

- increasing volatility

- worsening milestone performance

Method

Transparent statistical/rule-based score

For example:

Deterioration=w1Trend+w2Velocity+w3Deviation+w4Volatility

Weights should later be empirically tested.

PART G — SCHEDULE CALCULATIONS

33. Schedule slippage

For completed/updated projects:

Schedule Slippage=Actual/Latest Completion Date-Original Completion Date

Method

Formula

34. Schedule slippage %

Schedule Slippage%=Actual/Latest Duration-Planned DurationPlanned Duration×100

Method

Formula

35. Schedule overrun in months

Delaymonths=Actual/Forecast Completion-Planned Completion

Method

Formula for observed outcomes; ML for future prediction.

This distinction is extremely important.

36. Historical schedule-overrun label

For training:

1 = significant schedule overrun

0 = no significant schedule overrun

Method

Rule-based label creation

The threshold must be explicitly defined and justified.

For example, a threshold could be based on a specified number of months or a percentage of planned duration.

PART H — MILESTONE CALCULATIONS

Only use these if milestone-level data exists.

37. Milestone delay

Milestone Delay=Actual Milestone Date-Planned Milestone Date

Method

Formula

38. Number of delayed milestones

Delayed Milestones=COUNTMilestones with Delay>Threshold

Method

Counting/rule

39. Milestone delay %

Milestone Delay Rate=Delayed MilestonesTotal Completed/Due Milestones×100

Method

Formula

40. Average milestone delay

Average Milestone Delay=DelayiNumber of Delayed Milestones

Method

Formula

41. Milestone completion rate

Milestone Completion Rate=Completed MilestonesDue Milestones×100

Method

Formula

PART I — ISSUE / PROBLEM CALCULATIONS

42. Active issue count

Active Issues=COUNTOpen Issues

Method

Counting

43. Persistent issue duration

Issue Duration=Current Date-Issue Open Date

Method

Formula

44. Maximum issue duration

MaxIssueDuration=MAXIssueDurations

Method

Aggregation

45. Issue persistence rate

For example:

Issue Persistence=Issues Remaining OpenIssues Raised×100

Method

Formula

46. Issue recurrence

Count repeated issues associated with the same project/category.

Method

Counting/grouping

Why

Repeated unresolved issues are more informative than a simple raw issue count.

PART J — HISTORICAL PROJECT TRAJECTORY FEATURES

These are particularly important because your modern PAIMANA data can potentially be structured as project × month.

47. Previous-month progress

Progresst-1

Method

Data lookup

48. Previous-month expenditure

Expendituret-1

Method

Data lookup

49. 3-month progress change

ΔP3m=Pt-Pt-3

Method

Formula

50. 6-month progress change

ΔP6m=Pt-Pt-6

Method

Formula

51. 3-month expenditure change

ΔE3m=Et-Et-3

Method

Formula

52. Rolling average progress

3/6/12-month windows where enough data exists.

Method

Rolling statistics

53. Rolling average expenditure

Same.

Method

Rolling statistics

54. Rolling volatility

Calculate standard deviation over a recent window.

Method

Rolling statistics

55. Trend change

Compare recent slope with earlier slope:

TrendChange=Sloperecent-Slopeprevious

Method

Statistical calculation

This is a useful deterioration signal.

PART K — COST PREDICTION

Now we reach the point where ML becomes appropriate.

56. Probability of cost overrun

Question:

Given everything known about the project up to now, what is the probability that it will eventually experience significant cost overrun?

Method

Supervised ML classification

Recommended model

CatBoost Classifier

Why

Your data is primarily:

- tabular

- categorical

- numerical

- potentially nonlinear

- mixed project characteristics

- likely moderate in size

CatBoost handles categorical variables and nonlinear relationships particularly well.

Output:

PCost Overrun

Example:

0.78 = 78% predicted probability.

PART L — EXPECTED COST OVERRUN

57. Predicted final cost

Question:

What is the expected final/revised project cost?

Method

Supervised ML regression

Recommended model

CatBoost Regressor

58. Predicted cost overrun amount

Predicted Overrun=Predicted Final Cost-Original Cost

Method

ML + formula

The ML model predicts final cost; the overrun itself is then deterministically calculated.

59. Predicted cost overrun %

Predicted Overrun%=Predicted Final Cost-Original CostOriginal Cost×100

Method

ML + formula

This is an important example of where both methods work together.

60. Predicted cost exposure

At portfolio level:

Predicted Cost Exposure=Predicted Overrun Amount

Method

Aggregation of ML outputs

Not a new ML model.

PART M — SCHEDULE PREDICTION

61. Probability of schedule overrun

Question:

What is the probability that this project will exceed its planned schedule?

Method

Supervised ML classification

Recommended model

CatBoost Classifier

62. Predicted delay duration

Question:

If/when delayed, how much delay is expected?

Method

Supervised ML regression

Recommended model

CatBoost Regressor

63. Predicted completion date

Conceptually:

Predicted Completion=Current/Planned Completion+Predicted Delay

Method

ML + formula

The ML model predicts delay; the date calculation itself is deterministic.

64. Predicted schedule exposure

At portfolio level:

Schedule Exposure=Predicted Delay

or, more usefully, aggregate expected delay weighted by project importance where justified.

Method

Aggregation

PART N — POSSIBLE TIME-TO-EVENT MODEL

There is one additional model worth evaluating later.

65. Probability of completing within a future period

Instead of predicting a fixed delay directly, you can model:

probability of project completion within the next X months.

Method

Survival/time-to-event model

Potential approaches:

- survival analysis

- gradient-boosted survival model

Recommendation

Optional, not V1.

CatBoost classification/regression is simpler for your SIH prototype.

Only introduce survival modelling if your project-month data and censoring structure justify it.

PART O — ANOMALY DETECTION

66. Unusually high cost escalation

Calculate project cost escalation percentile or robust z-score relative to peers.

Method

Statistics

67. Unusually high expenditure

Compare expenditure against peer/project trajectory distribution.

Method

Robust statistics

68. Unusual progress/expenditure relationship

For example:

expenditure is extremely high relative to physical progress.

Method

Statistical anomaly detection

69. Multivariate project anomaly

Detect projects that are unusual across multiple dimensions simultaneously.

Method

Isolation Forest

Why

Unlike a simple threshold, Isolation Forest can identify unusual combinations of features.

Important

This is anomaly detection, not prediction.

70. Robust z-score

For a variable:

zrobust=x-Medianx1.4826×MAD

Method

Robust statistics

Better than ordinary z-score when project data contains extreme outliers.

71. Percentile-based anomaly

Example:

Project is in the 99th percentile of cost escalation within its peer group.

Method

Percentile calculation

This is often easier to explain to government users than a black-box anomaly score.

PART P — PROJECT RISK

This should not be another ML model initially.

72. Cost risk

Derived from:

- predicted probability of cost overrun

- predicted overrun magnitude

- current cost escalation

- exposure

Method

Risk transformation + formula

73. Schedule risk

Derived from:

- predicted schedule-overrun probability

- predicted delay

- current schedule slippage

- progress deviation

Method

Risk transformation + formula

74. Progress risk

Derived from:

- progress deviation

- progress trend

- progress velocity

- deterioration

Method

Statistical/rule-based score

75. Milestone risk

Derived from:

- delayed milestone count

- milestone delay

- milestone completion rate

Method

Formula/rule

76. Issue risk

Derived from:

- active issue count

- persistent issue duration

- recurring issues

Method

Formula/rule

77. Overall project risk score

Conceptually:

Risk=wcC+wsS+wpP+wmM+wiI

where:

- C= cost risk

- S= schedule risk

- P= progress risk

- M= milestone risk

- I= issue risk

Method

Transparent weighted risk engine

Why not ML?

Because the risk score is a decision framework, not necessarily an unknown outcome.

You want administrators to understand:

“This project is High Risk because schedule and cost risk are elevated.”

rather than:

“Another neural network says it is 82% risky.”

Important

The weights should eventually be:

- benchmarked

- sensitivity-tested

- calibrated against historical outcomes where possible

Do not simply invent weights and treat them as scientifically established.

PART Q — RISK BAND

78. Risk band

Convert continuous risk into:

- Low

- Moderate

- High

- Critical

Method

Threshold/rule

Example:

0–25       Low

25–50      Moderate

50–75      High

75–100     Critical

But these exact thresholds should not be assumed. They should be calibrated/tested.

PART R — RISK DETERIORATION

79. Risk change

RiskChange=Riskt-Riskt-1

Method

Formula

80. Risk deterioration %

RiskDeterioration%=Riskt-RiskpreviousRiskprevious×100

Method

Formula

81. Risk trajectory

Use recent risk-score slope.

Method

Statistical trend

82. Risk acceleration

RiskAcceleration=RiskVelocityt-RiskVelocityt-1

Method

Formula

This helps distinguish:

risk increasing slowly

from:

risk increasing rapidly.

PART S — RISK DRIVERS

83. Model-based risk/prediction drivers

For ML predictions:

Method

SHAP

For example:

Schedule risk increased primarily because of low recent progress, prolonged issue duration, and historical schedule performance.

Why

SHAP provides local feature attribution for tree-based models.

84. Statistical risk drivers

For deterministic risk:

Use:

- trend

- deviation

- threshold breaches

- persistent issues

- milestone delays

Method

Rule-based evidence extraction

Do not call these “causes” unless causal analysis has actually been performed.

Use:

Contributing factors

or

Associated drivers

PART T — EARLY WARNING

85. Warning trigger

Example:

IF schedule probability > threshold

AND predicted delay > threshold

THEN Schedule Warning

Method

Rule engine

Why

Warnings are policy/decision logic. They need to be understandable and auditable.

86. Warning severity

Possible:

- Informational

- Low

- Moderate

- High

- Critical

Method

Rule-based classification

87. Warning urgency

Can consider:

- risk

- predicted delay

- remaining time

- persistence

- deterioration rate

Method

Decision formula/rules

88. Warning persistence

Warning Persistence=Current Date-Warning Start Date

Method

Formula

89. Warning status

Examples:

- New

- Active

- Escalated

- Resolved

- Dismissed

Method

State machine / business rules

Not ML.

PART U — INTERVENTION PRIORITY

90. Intervention priority score

Conceptually:

Priority=Risk×Exposure×Urgency×Persistence

with appropriately normalized components.

Method

Transparent decision score

Why

The ML model should tell you:

“This project is likely to have a problem.”

The intervention engine decides:

“Which problematic project deserves attention first?”

Those are different tasks.

91. Intervention ranking

Sort projects by intervention priority.

Method

Ranking

No new ML model.

92. Intervention recommendation

Example:

Persistent land-acquisition issue → escalation/review by relevant authority.

Method

Rule/knowledge mapping

Not an ML prediction.

Since your current architecture has LLM out of scope, keep this deterministic.

PART V — COST DRIVER ANALYSIS

93. Cost-driver association

Identify variables associated with higher cost overrun.

Method

Combination of:

- statistical analysis

- correlation

- regression

- group comparisons

- SHAP

Important

Do not write:

“Land acquisition causes cost escalation.”

unless causal analysis establishes that.

Instead:

“Land acquisition delay is associated with higher observed cost escalation.”

94. Global feature importance

Method

SHAP / model feature importance

Shows which variables are generally influential in the cost model.

95. Project-specific feature contribution

Method

SHAP

Answers:

Why did the model give this project a high cost-overrun prediction?

PART W — SECTOR / MINISTRY / STATE AGGREGATION

These dashboards should not train separate models merely because they display different dimensions.

They consume project-level outputs.

96. Project count

Project Count=COUNTDISTINCT ProjectID

Method

Aggregation

Critical nuance

Do not count monthly project records.

97. Total approved/original cost

Total Cost=Original Project Cost

Method

SUM

98. Total revised cost

Total Revised Cost=Revised Project Cost

Method

SUM

99. Portfolio cost escalation

RevisedCost-OriginalCostOriginalCost×100

Method

Weighted aggregate formula

This is preferable to averaging project-level escalation percentages.

100. Total expenditure

Total Expenditure=Cumulative Expenditure

Method

SUM

101. Portfolio expenditure %

ExpenditureRelevantCost×100

Method

Weighted ratio

Again, don't simply average individual project expenditure percentages.

102. Average physical progress

MeanProgress=PhysicalProgressN

Method

Arithmetic mean

But if appropriate, also provide weighted measures.

103. Median physical progress

Method

Median

Why

Infrastructure data can contain extreme projects. Median provides a more robust central measure.

104. Average cost escalation %

Method

Mean

Useful for the typical project, but should be distinguished from portfolio-level escalation calculated from aggregate costs.

105. Median cost escalation %

Method

Median

Useful for reducing the influence of extreme projects.

106. High-risk project count

COUNTRiskBand∈HighCritical

Method

Counting

107. Critical project count

COUNTRiskBand=Critical

Method

Counting

108. Warning count

COUNTActiveWarnings

Method

Counting

109. Deteriorating project count

COUNTDeterioratingProjects

Method

Rule-based counting

PART X — PORTFOLIO PREDICTIVE AGGREGATIONS

110. Predicted cost exposure

PredictedOverrunAmount

Method

Aggregation of ML predictions

111. Average predicted cost overrun

MeanPredictedOverrun%

Method

Statistical aggregation

112. Expected cost exposure

A more probabilistically sound measure can be:

Expected Cost Exposure=PiCostOverrun×ExpectedOverrunAmounti

Method

Probability × predicted magnitude + aggregation

Why

This can be more informative than simply summing predicted overrun amounts.

It incorporates uncertainty.

113. Average predicted delay

MeanPredictedDelay

Method

Aggregation

114. Total predicted delay exposure

PredictedDelay

Method

Aggregation

115. Expected schedule exposure

Potentially:

ExpectedScheduleExposure=PiScheduleOverrun×PredictedDelayi

Method

Probability-weighted aggregation

This is preferable if your two schedule models are well calibrated.

PART Y — RANKINGS

116. Sector ranking

Rank sectors based on selected metric.

Method

Aggregation + sorting/ranking

Possible ranking metrics:

- highest cost escalation

- highest predicted exposure

- highest risk count

- highest delay exposure

- most deteriorating projects

117. Ministry ranking

Same.

Method

Aggregation + ranking

118. Agency ranking

Same.

Method

Aggregation + ranking

119. State ranking

Same.

Method

Aggregation + ranking

120. Project ranking

Rank projects by:

- overall risk

- predicted cost exposure

- predicted delay

- intervention priority

- deterioration

Method

Score + sorting

No new ML model.

PART Z — TRENDS ON ANALYTICAL DASHBOARDS

121. Monthly project count

COUNTDISTINCTProjectID

Method

Aggregation

122. Monthly investment

SUMProjectCost

Method

Aggregation

123. Monthly expenditure

SUMExpenditure

Method

Aggregation

124. Monthly average progress

Method

Aggregation

125. Monthly risk trend

MeanRiskScoret

Method

Aggregation

126. High-risk trend

CountHigh/Criticalt

Method

Counting + time aggregation

127. Warning trend

CountWarningst

Method

Counting + time aggregation

PART AA — BENCHMARKING

128. Sector benchmark

Compare project/sector performance against portfolio.

Example:

SectorCostEscalation-PortfolioCostEscalation

Method

Aggregation + comparison

129. Ministry benchmark

Same.

Method

Aggregation + comparison

130. State benchmark

Same.

Method

Aggregation + comparison

131. Peer-project benchmark

Compare a project against projects with similar:

- sector

- size

- stage

- geography

- project type

Method

Statistical peer-group comparison

Why

Comparing a ₹10,000 crore project against a ₹150 crore project without context can be misleading.

PART AB — MODEL PERFORMANCE CALCULATIONS

These don't calculate project figures directly, but they are required to determine whether your intelligence engine is reliable.

132. Precision

Precision=TPTP+FP

Method

Statistical evaluation

Important for avoiding excessive false warnings.

133. Recall

Recall=TPTP+FN

Important because missing a genuinely deteriorating project can be costly.

134. F1

F1=2Precision×RecallPrecision+Recall

135. ROC-AUC

Method

Classification evaluation

136. PR-AUC

Method

Classification evaluation

Particularly useful if actual overruns are relatively uncommon.

137. Calibration

Compare predicted probabilities with observed frequencies.

Method

Calibration analysis

This is very important because you're using probabilities to generate risk/warning thresholds.

138. MAE

MAE=1N∣yi-yi∣

Method

Regression evaluation

139. RMSE

RMSE=1N(yi-yi)2

Method

Regression evaluation

140. False-warning rate

FWR=False WarningsTotal Warnings

Method

Formula

Extremely relevant to your Early Warning system.

141. Lead time

Lead Time=Actual Problem Date-Warning Date

Method

Formula

Why

A warning system isn't useful merely because it is accurate.

It needs to warn early enough to act.

PART AC — DATA QUALITY CALCULATIONS

These belong in Data & Model Operations.

142. Missing-value rate

MissingRate=MissingValuesTotalExpectedValues×100

Method

Formula

143. Duplicate rate

DuplicateRate=DuplicateRecordsTotalRecords×100

Method

Formula

144. Validation pass rate

ValidationPassRate=ValidRecordsTotalRecords×100

Method

Formula

145. External dataset match rate

MatchRate=SuccessfullyMatchedRecordsEligibleRecords×100

Method

Formula

This is particularly important for WPI or future external datasets.

PART AD — DATA/MODEL MONITORING

These are useful later.

146. Feature distribution shift

Compare feature distributions between training and new data.

Method

Statistical drift detection

Possible methods:

- PSI

- KS statistic

- distribution distance measures

147. Prediction distribution shift

Compare current predictions with previous production predictions.

Method

Statistical distribution comparison

148. Model performance drift

Compare recent labelled outcomes with historical model performance.

Method

Statistical evaluation

149. Data coverage

Coverage=ProjectsWithRequiredDataTotalProjects×100

Method

Formula

PART AE — GEOGRAPHIC / PORTFOLIO SPECIAL CASES

These are important for your State Analytics.

150. State project count

COUNTDISTINCTProjectID

Method

Aggregation

But multi-state projects need special handling.

151. Multi-state project handling

A project genuinely spanning multiple states can appear in each relevant State view.

Method

Data attribution rule

Critical nuance

Do not sum the same project's full cost across states and then call that India's/state portfolio investment without accounting for duplication.

If the source does not provide defensible state-level cost allocation:

show project association in each relevant state, but do not fabricate a cost split.

PART AF — HOME DASHBOARD CALCULATIONS

The Home dashboard should be comparatively simple.

152. Projects monitored

COUNTDISTINCTProjectID

153. Approved cost

SUMOriginalApprovedCost

154. Revised cost

SUMLatestRevisedCost

155. Overall portfolio cost growth

RevisedCost-OriginalCostOriginalCost×100

156. Cumulative expenditure

SUMCumulativeExpenditure

157. Expenditure as % of revised cost

ExpenditureRevisedCost×100

158. Projects requiring attention

Count projects satisfying your approved attention criteria.

Method

Rule-based counting

Not another model.

159. Risk concentration map

For each geographic unit:

- project count

- high-risk count

- critical-risk count

- risk density

Method

Aggregation

The most important distinction in the whole architecture

You effectively have three layers of numbers.

Layer 1 — What has actually happened

Examples:

- Original cost

- Revised cost

- Expenditure

- Physical progress

- Time elapsed

- Cost escalation

- Schedule slippage

- Milestone delay

Method: formulas/source data.

Layer 2 — What the system thinks will happen

Examples:

- Probability of cost overrun

- Expected final cost

- Predicted cost overrun

- Probability of schedule overrun

- Predicted delay

- Predicted completion date

Method: ML.

Your initial model family should be:

CatBoost classification + CatBoost regression

with simpler statistical baselines used for benchmarking.

Layer 3 — What the system recommends prioritizing

Examples:

- Overall risk

- Risk band

- Warning

- Warning severity

- Deterioration

- Intervention priority

Method: transparent statistical/rule-based decision engine.

Final master map

If I compress the entire architecture into one table:

| Intelligence / Figure | Optimal method |
| --- | --- |
| Project duration | Formula |
| Elapsed duration | Formula |
| Remaining duration | Formula |
| Time elapsed % | Formula |
| Cost escalation | Formula |
| Cost escalation % | Formula |
| Expenditure % | Formula |
| Remaining financial exposure | Formula |
| Physical progress | Source data |
| Financial progress | Formula/source |
| Physical-financial gap | Formula |
| Expected progress | Formula/statistical baseline |
| Progress deviation | Formula |
| Progress velocity | Formula |
| Expenditure velocity | Formula |
| Progress acceleration | Formula |
| Expenditure acceleration | Formula |
| Progress trend | Statistical regression |
| Expenditure trend | Statistical regression |
| Moving averages | Rolling statistics |
| Volatility | Standard deviation |
| Deterioration | Statistical/rule score |
| Schedule slippage | Formula |
| Schedule overrun | Formula for observed outcome |
| Milestone delay | Formula |
| Delayed milestone count | Counting |
| Milestone completion rate | Formula |
| Active issue count | Counting |
| Issue duration | Formula |
| Issue persistence | Formula |
| Historical trajectory | Rolling statistics |
| Cost-overrun probability | CatBoost classifier |
| Expected final cost | CatBoost regressor |
| Predicted cost overrun | ML + formula |
| Predicted cost overrun % | ML + formula |
| Schedule-overrun probability | CatBoost classifier |
| Predicted delay | CatBoost regressor |
| Predicted completion | ML + formula |
| Anomaly score | Robust statistics / Isolation Forest |
| Risk drivers | SHAP + deterministic evidence |
| Cost drivers | Statistics + SHAP |
| Cost risk | Risk engine |
| Schedule risk | Risk engine |
| Progress risk | Risk engine |
| Milestone risk | Risk engine |
| Issue risk | Risk engine |
| Overall risk | Transparent weighted risk engine |
| Risk band | Threshold rules |
| Risk deterioration | Formula + trend |
| Warning trigger | Rule engine |
| Warning severity | Rule engine |
| Warning urgency | Rule/decision score |
| Warning persistence | Formula |
| Intervention priority | Transparent decision score |
| Intervention recommendation | Rule/knowledge mapping |
| Project ranking | Score + sorting |
| Sector ranking | Aggregation + ranking |
| Ministry ranking | Aggregation + ranking |
| Agency ranking | Aggregation + ranking |
| State ranking | Aggregation + ranking |
| Portfolio trends | Aggregation/statistics |
| Portfolio cost exposure | Aggregation |
| Expected cost exposure | Probability-weighted aggregation |
| Expected schedule exposure | Probability-weighted aggregation |
| Peer benchmark | Statistical comparison |
| Data quality | Formula/statistics |
| Model performance | Statistical evaluation |
| Model drift | Statistical monitoring |

The architecture I would ultimately put in your technical specification

PAIMANA DATA

│

▼

┌─────────────────────┐

│ Deterministic Layer │

│ formulas / counts   │

│ ratios / dates      │

└──────────┬──────────┘

│

▼

┌─────────────────────┐

│ Temporal Statistics │

│ trends / velocity   │

│ rolling stats       │

│ deterioration       │

└──────────┬──────────┘

│

▼

┌─────────────────────┐

│    ML Prediction    │

│                     │

│ Cost classifier     │

│ Cost regression     │

│ Schedule classifier │

│ Delay regression    │

└──────────┬──────────┘

│

▼

┌─────────────────────┐

│    Risk Engine      │

│ cost + schedule +   │

│ progress + issues   │

└──────────┬──────────┘

│

▼

┌─────────────────────┐

│   Warning Engine    │

│ rules + prediction  │

│ + deterioration     │

└──────────┬──────────┘

│

▼

┌─────────────────────┐

│ Intervention Engine │

│ priority + evidence │

└──────────┬──────────┘

│

▼

┌─────────────────┼─────────────────┐

▼                 ▼                 ▼

Project           Early Warning    Aggregation

Intelligence                         dashboards

│

┌────────────┼────────────┐

▼            ▼            ▼

Sector       Ministry      State

One major recommendation

Do not try to make every one of these calculations a separate “feature” visible on the UI. Many are intermediate computational features used by other calculations or models.

For example:

Progress velocity → progress trend → deterioration → risk → warning → intervention priority

The user may only see “Deteriorating” and the evidence behind it. The underlying velocity, slope, moving average, etc. can remain computational features.

Likewise:

Cost classifier + cost regression → predicted probability + predicted magnitude → expected cost exposure

This keeps your actual dashboards relatively clean while the backend intelligence layer can be extremely comprehensive.

And crucially, I would not commit all the proposed formulas/thresholds/weights as final yet. Your March 2025+ PAIMANA data should be used to test which features actually exist, which are reliable, which have enough longitudinal coverage, and which thresholds/weights/models perform best. The computational architecture above can be your V1 specification, while the exact parameters become part of your later benchmarking/validation phase.